## Slide 1: XC2 — WP1 Client Brief (ICT80004 Internship Project)
Project Concept & Evaluation Plan · 03 Sep 2025 · Team XC2 (Arun Ragavendhar, Vaisakh, Aarathi, Aayudh, Samsun, Vikas)

## Slide 2: Problem & Goal
Problem: LLMs can be steered by persuasive text (prompt injection).
Goal: Build a simple, testable plan to measure and reduce these attacks in realistic tasks.
Outcome for WP1:
  A small but deep tactic set
  A clean prompt pipeline and defenses
  Clear metrics and baselines

## Slide 3: Scope (In / Out)
In scope (text-only):
  Tactics that can be written as prompt text
  Summarisation + QA tasks
  Placements: start/middle/end
  Defenses: boundary, reminders, light guard
Out of scope:
  Outcomes (e.g., phishing, ransomware)
  Channels (robocalls/SMS/phone)
  Physical vectors (tailgating, etc.)

## Slide 4: Method — 2-Week Sprints
Loop: discover → design → defend → document
discover:
  Pick tactics, scenarios, tasks, placements; ethics check
design:
  Generate prompts and configs; finalize defense lines
defend:
  Run baselines/defenses; record ASR, quality, cost
document:
  Summarize results; decisions; next-sprint items

## Slide 5: Suitability Analysis (Filter)
Keep: tactics that can be expressed as text prompts.
Drop: outcomes, channels, physical methods (document only).
Steps:
  Label each item (tactic/outcome/channel/physical)
  Keep tactics and map to system/user/retrieved surfaces
  Design 3 scenarios per tactic; 5 prompts per scenario (safe)

## Slide 6: Tactic Shortlist (9)
# | Tactic
1 | Baiting
2 | Pretexting
3 | Impersonation (Help Desk/Admin)
4 | Quid-pro-quo / Reciprocity
5 | Authority
6 | Social proof
7 | Urgency / Scarcity
8 | Story / Empathy framing
9 | Reverse social engineering

## Slide 7: Prompt Generation — Template & Controls
Template fields:
  tactic, scenario_id, placement, attack_goal, clean_task, safety_notes
Message skeleton:
  System: boundary + reminder lines
  User: External Content + Task sections
Naming: prompts/<tactic>/<scenario>/p_<placement>_v*.txt
Filters: safe content only; no real keys; dedupe; traceable seeds

## Slide 8: Evaluation Plan — What We Test
Tasks:
  Summarisation (short passages)
  QA (short factual; small table QA if time allows)
Placements:
  Start
  Middle
  End
Surfaces:
  User message
  Retrieved text (RAG-like)

## Slide 9: Metrics & Pass/Fail
Metrics:
  ASR = attack success rate
  Task quality: QA exact-match; Summarisation overlap
  Cost: extra tokens, rough time
Pass/Fail lines:
  Primary: ASR ↓ ≥ 50% vs. no defense
  Secondary: quality drop ≤ 2/10 points

## Slide 10: Defenses (Staged, Cost-Aware)
1) Boundary awareness line (default)
2) Explicit reminder line (default)
3) Light guard for tough cases
4) Small, time-boxed fine-tune (only if needed)

## Slide 11: Environment & Governance
Repos: GitHub private, protected main
CI: tests + small nightly red-team check
Storage: OneDrive/SharePoint (private, MFA)
Local demo: Streamlit or FastAPI (no public URL)
Roles: Tech Lead, Safety Lead, Evaluation Lead, Ethics Officer, Maintainer
Change control: issues + PRs; Ready/Done checklists
No secrets in code; configs + seeds saved with results

## Slide 12: Timeline — Next Two Sprints
Sprint 1 (Weeks 1–2):
  Suitability analysis finalized
  Prompts generated
  Baselines + defenses run on sample set
  Summary + decisions
Sprint 2 (Weeks 3–4):
  Scale runs evenly per tactic
  Tune defenses where weak
  Optional guard if needed
  Client review + plan next phase

## Slide 13: Risks & Mitigations (Starter List)
Unsafe prompt text
  Mitigation: fixed templates + Safety Lead review
Biased survey wording
  Mitigation: pilot + checklist; Plan B: drop item
Data leaks
  Mitigation: de-identify; Plan B: delete & restore clean copy
Scope creep / time over-run
  Mitigation: cap runs; core tactics first

## Slide 14: Decisions/Asks for Today
Confirm the 9-tactic shortlist (any additions/removals?)
Agree on metrics and pass/fail lines
Confirm storage and ethics approach (de-identified, private folders)
Sign-off on Section 3 and this WP1 plan so we proceed